## schedule
Week | StartDate | EndDate | Task | Description | Status
1-2 | 2016-09-01 | 2016-09-17 | Start-up | Set up program enviroment and design project
3 | 2016-09-18 | 2016-09-24 | Develop | Start developing project codes and testscripts
4 | 2016-09-25 | 2016-10-01 | Refine | Refine project codes
5 | 2016-10-02 | 2016-10-08 | Release 1 | Release first version of project
6 | 2016-10-09 | 2016-10-15 | Review | Review release 1 and consider improvement
7-8 | 2016-10-16 | 2016-10-29 | Release 2 | Improve release 1 and release second version of project
9-12 | 2016-10-30 | 2016-11-19 | Release 3 | Complete all outstanding issues of project and develop final version
13-14 | 20/11/0216 | 2016-12-03 | Rollout | Demostration of final version of project

## member
Member | Role | EID | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14 | Total
Li Ho Yeung | Programmer |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Vun Yiu Hin | Programmer |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Ng Tsz Ho | Programmer |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Liu Chun Hin | Project Manager | 5403 4069 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Liu Ka Wing | Configuration Manager |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Chung Chor Yi | Testing Engineer |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Lao Cheuk Hin | Testing Engineer |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%

## progress log
Week | Task ID | Task | Description | status
1 | 1a | Groupping | Finding group members | Finish
| 1b | Brain Storming | Brainstorm on project topic | Finish
2 | 2a | Design Topic | Design on the Project topic | Finish
| 2b | Initial Plan | Thinking about Project details | Finish
3 | 3a | Scope | Define Project scope
| 3b | Estimate | Estimation of project
| 3c | Constraints | Define any constaints of project development
4 | 4a | Start-up | Setup coding environment
| 4b | Code Planning | Planning the basic coding of project
| 4c | Structual Design | Plan for the file and data structure of project
5 | 5a | Development - 1 | Develop Prototype of project
| 5b | Testing | Basic testing of project
6 | 6a | Release 1 | Release first version of project
| 6b | Brief Planning | Write 4-page bried project planning
| 6c | Release Summary | Write 1-page release summary
| 6d | Analysis | Prepare project analysis and design report
7 | 7a | Review | Review release 1 for improvement
| 7b | Testing | Test for outstanding issues in review
8 | 8a | Detail Planning | Complete project planning with details
| 8b | Debugging | Debug with release 1 and produce bug report
| 8c | Development - 2 | Add other functions for project and complete project code
9 | 9a | Release 2 | Release second version of project
| 9b | Produce Report | write detailed project analysis and design report
| 9c | Testing | Test for finding any final outstanding issues
10 | 10a | Documentation | Complete all related reports and documents
| 10b | Debugging | Fix all outstanding issues of project code
11 | 11a | Release 3 | Produce final version of project
12 | 12a | Demostration | Demonstration of project